Republic of Tajikistan

State Committee for Investment and State Property Management

FINGROW Tajikistan (P512525)

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

Draft for Appraisal

April 10-2025

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Republic of Tajikistan (the Recipient) will implement the FINGROW Tajikistan Project (the Project), with the involvement of the State Committee for Investment and State Property Management of the Republic of Tajikistan, as set out in the Grant agreement (the Grant Agreement). The International Development Association (the Association) has agreed to provide financing for the Project, as set out in Agreement.

- The Recipient shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this Environmental and Social Commitment Plan (ESCP), in a manner acceptable to the Association. The ESCP is a part of the Grant Agreement. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the Grant Agreement.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Recipient shall carry out or cause to be carried out, including, as applicable, their respective timeframes; institutional, staffing, training, monitoring and reporting arrangements; and grievance management. The ESCP also sets out the environmental and social (E&S) documents that shall be prepared or updated, consulted, disclosed and implemented under the Project, consistent with the ESSs, in form and substance acceptable to the Association. Said E&S documents may be revised from time to time with prior written agreement by the Association. As provided for under the referred Grant Agreement, the Recipient shall ensure that there are sufficient funds available to cover the costs of implementing the ESCP.

- As agreed by the Association and the Recipient, this ESCP will be revised from time to time, if necessary, to reflect adaptive management of Project changes or unforeseen circumstances or in response to Project performance. In such circumstances, the Association and the Recipient agree to update the ESCP to reflect these changes through an exchange of letters signed between the Association and the Recipient’s Representative specified in the Grant Agreement or Director of the Project Implementation Unit of the project. The  Recipient shall promptly disclose the updated ESCP.

- The subsection on “Indicators for Implementation Readiness” below identifies the actions and measures to be monitored to assess Project readiness to begin implementation in accordance with this ESCP. Nevertheless, all actions and measures in this ESCP shall be implemented as set out in the “Timeframe” column below irrespective of whether they are listed in the referred subsection.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBLE ENTITY |
| --- | --- | --- | --- |
| IMPLEMENTATION ARRANGEMENTS AND CAPACITY SUPPORT |  |  |  |
| A | ORGANIZATIONAL STRUCTURE - Establish and maintain a Project Implementation Unit (PIU) with existing qualified staff and adequate resources to support management of environmental, social, health and safety (ESHS) risks and impacts of the Project including one Social Specialist and one Environmental Specialist. - Review staffing needs during the Project implementation and engage short-term staff/consultants as needed. | a. Maintain the Project Implementation Unity (PIU) as set out in the Grant Agreement. Specialists of the PIU responsible for Environmental and Social (E&S) oversight shall be recruited prior to Project Effectiveness. b. Throughout Project implementation. | SCI/PIU |
| B | CAPACITY BUILDING PLAN/MEASURES Prepare and implement a capacity building plan identifying target participants, training topics, schedule, and delivery methods for targeted groups who require the training on: - E&S assessment (screening and scoping); - Community health and safety and ICWMP; - Orientation training on implementing the various provisions of ESF and ESMF; - Implementation progress and monitoring report on ESMPs implementation compliance; - Specific aspects of E&S risks, occupational and community health and safety; - Implementation of LMP, its provisions, and labor complaints management; - The ESMF and RF prepared for the Project; - Stakeholder identification, engagement and GM; - Specific aspects of E&S impact assessment; - Prevention of and response to SEA/SH; | Throughout the project implementation. | SCI/PIU |
| MONITORING AND REPORTING |  |  |  |
| C | REGULAR REPORTING Prepare and submit to the Association regular monitoring reports on environmental, social, health and safety (E&S) performance of the Project, including but not limited to the implementation of the ESCP, status of preparation and implementation of E&S documents required under the ESCP, summary of stakeholder engagement activities carried out as per the Stakeholder Engagement Plan, and functioning of the grievance mechanism(s), and the application of environmental and social risk management measures, and labor management procedures. | Submit quarterly reports to the Association throughout Project implementation, commencing after the Effectiveness Date. Submit each report to the Association no later than 15 days after the end of each reporting period. | SCI/PIU |
| D | CONTRACTORS’ MONTHLY REPORTS Require contractors and supervising firms to provide monthly monitoring reports on E&S performance in accordance with the metrics specified in the respective bidding documents and contracts and submit such reports to the Association. | Submit the reports to the Association as annexes to the reports to be submitted under action C above | SCI/PIU |
| E | INCIDENTS AND ACCIDENTS Promptly notify the Association of any incident or accident relating to the project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers, including, inter alia, cases of sexual exploitation and abuse (SEA), sexual harassment (SH), fatalities, serious injuries, , environmental pollution, or security incidents. Initial notification shall be made immediately and no later than 48 hours after becoming aware of the incident. Notification shall include review of the incident or accident regarding the nature, scope, severity, and possible causes of the incident, to establish its immediate, underlying and root causes. Prepare, agree with the Association, and implement a Corrective Action Plan that sets out the measures and actions to be taken to address the incident or accident and prevent its recurrence. Maintain an incident register at all Project sites and ensure contractors report incidents promptly to the PIU. Ensure that incident reporting requirements are included in all contractor ESMPs and contracts, consistent with the World Bank Environmental and Social Incident Response Toolkit (ESIRT). | Notify the Association no later than 48 hours after learning about the incident or accident. Provide available details upon request. Provide review report and Corrective Action Plan to the Association, no later than 10 days following the submission of the initial notice, unless a different timeframe is agreed to in writing by the Association. | SCI/PIU |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ENVIRONMENTAL AND SOCIAL ASSESSMENTS AND/OR PLANS 1. Prepare and implement the Environmental and Social Management Framework (ESMF) and Environmental and Social Management System (ESMS) for the Project, consistent with the relevant ESSs. Screen all subprojects in accordance with the ESMF and prepare site-specific ESMPs as required. 2. Prepare, disclose, adopt and implement an Environmental and Social Management Plan (ESMP) for the Project, as set out in ESMF. | 1. Prepare, consult on, and disclose the ESMF and ESMS within 60 days of Effective Date and before the launch of any procurement process. Thereafter implement the ESMF and ESMS throughout Project implementation. 2. Prepare, consult on, disclose, and obtain the Association’s clearance of site-specific ESMPs prior to launching the bidding process for any works and prior to commencement of any renovation activities at the respective sites. | SCI/PIU |
| 1.2 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESCP, including, inter alia, the relevant E&S documents, the Labor Management Procedures, and Code of Conduct, into the E&S specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply and that they require their subcontractors to comply with the E&S specifications of their respective contracts. Provide copies of the relevant contracts with contractors/subcontractors to the Association. Ensure contractors prepare, adopt, and implement Contractor ESMPs (C-ESMPs), consistent with site-specific ESMPs. | Prior to engaging Project workers and thereafter implement throughout Project implementation.. As part of the preparation of procurement documents and respective contracts. Supervise contractors throughout Project implementation. | SCI/PIU |
| 1.3 | TECHNICAL ASSISTANCE Ensure that the consultations, studies (including feasibility studies, if applicable), capacity building, training, and any other technical assistance activities under the Project are carried out in accordance with terms of reference acceptable to the Association, that are consistent with the ESSs. Thereafter prepare and finalize the outputs of such activities in compliance with the terms of reference. Ensure outputs of technical assistance are consistent with ESSs. | Throughout Project implementation. | SCI/PIU |
| ESS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURES Prepare, adopt and implement the Labor Management Procedures (LMP) applicable to the entire Project including, inter alia, provisions on working conditions, occupational, health and safety, code of conduct, workers grievance mechanism, and applicable requirements for contractors, subcontractors, and supervising firms (including relevant national laws and other ESS2 requirements, such as adoption of a code of conduct, prevention of all forms of forced labor and child labor). | As part of the preparation of procurement documents and respective contracts. Supervise contractors and implement the LMP throughout Project implementation. | SCI/PIU |
| 2.2 | OCCUPATIONAL HEALTH AND SAFETY MANAGEMENT PLAN Implement Occupational, Health and Safety (OHS) measures as per applicable national law, ESS2 and guidelines specified in the subproject specific ESMPs and LMP. | Implement the OHS throughout Project implementation. Include emergency preparedness and response measures as part of OHS management. | SCI/PIU |
| 2.3 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Establish and operate a grievance mechanism for Project workers, as described in the LMP and consistent with ESS2. | Establish grievance mechanism prior engaging Project workers and thereafter maintain and operate it throughout Project implementation. | SCI/PIU |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | WASTE MANAGEMENT PLAN Prepare and implement an Infection Control Waste Management Plan (ICWMP), as part of the ESMP prepared for the Project, to manage hazardous and non-hazardous waste, including the e-waste including procedures for storage, transportation, treatment, and disposal of hazardous and non-hazardous waste consistent with ESS3. | Adopt the ICWMP and implement it throughout the project implementation period. | SCI/PIU |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT Incorporate resource efficiency and pollution prevention and management measures in the ESMP to be prepared under action 1.1 above. | During designing process and thereafter implement it throughout the project implementation stage. | SCI/PIU |
| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| 4.1 | COMMUNITY HEALTH AND SAFETY Assess and manage specific risks and impacts to the community arising from Project activities and include mitigation measures addressing SEA/SH risks, emergency response, and community exposure to project hazard in the ESMPs to be prepared in accordance with the ESMF. | Implement the ESMPs and its relevant provisions related to Traffic and Road throughout the project implementation period. | SCI/PIU |
| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT |  |  |  |
| ESS5 is not relevant |  |  |  |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES |  |  |  |
| ESS6 is not relevant |  |  |  |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES |  |  |  |
| ESS7 is not relevant |  |  |  |
| ESS 8: CULTURAL HERITAGE |  |  |  |
| ESS8 is not relevant |  |  |  |
| ESS 9: FINANCIAL INTERMEDIARIES |  |  |  |
| 9.1 | ENVIRONMENTAL AND SOCIAL MANAGEMENT SYSTEM (ESMS) Establish, adopt, and implement an Environmental and Social Management System (ESMS) consistent with ESS9, including screening, risk classification, monitoring, and reporting procedures. | Adopt the ESMS and thereafter, implement it throughout the project implementation period. |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN Update and implement a Stakeholder Engagement (EP) for the Project, consistent with ESS10, which shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. | Prepare, disclose, consult upon, adopt, and implement the SEP prior to Appraisal and maintain it throughout Project implementation. | SCI/PIU |
| 10.2 | PROJECT GRIEVANCE MECHANISM Establish, publicize, maintain, and operate an accessible grievance mechanism, to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of SEA/SH complaints, including through the referral of survivors to relevant gender-based violence service providers, all in a safe, confidential, and survivor-centered manner. | Establish the grievance mechanism by the project Appraisal and thereafter maintain and operate the mechanism throughout Project implementation. Maintain a grievance log and ensure timely resolution of grievances in accordance with defined service standards. |  |
| INDICATORS FOR IMPLEMENTATION READINESS [This subsection lists the ESCP actions (by their numbering in the first column of the ESCP) that are identified as relevant to monitor project readiness from an E&S standpoint. These may include actions related to: i) establishment of E&S risk management units in the Project Implementation Entities, ii) recruitment and training of E&S staff within Project Implementation Entities, iii) Memorandums of Understanding or other written agreements/arrangements between Project Implementation Entities and other concerned agencies to ensure proper coordination of E&S risk management activities; iv) E&S effectiveness or disbursement conditions, if deemed warranted, v) ES assessments and plans to be prepared by the Borrower at the onset of implementation; vi) other project-specific requirements related to E&S readiness for implementation]. |  |  |  |
| The following actions are indicators for implementation readiness: Organizational Structure (Action A) Capacity Support (B) Regular Reporting (Action C) Project Grievance Mechanism (Action 10.2) |  |  |  |